CTO

# App Charts & Tables
Video-Derived Inventory

Source basis: the three uploaded application videos only

Arrangement: Portfolio Command Center → CTO Analysis → Projects → Executive → Forecast Engineering → Cost Structure → Ledger & Controls → Source & Assurance

Format used throughout: CHART / TABLE NAME → SIGNALS → SHORT SUBTITLE EXPLANATION

# Master Application Arrangement

1. Portfolio Command Center

2. CTO Analysis

3. Projects

4. Executive

5. Forecast Engineering

6. Cost Structure

7. Ledger & Controls

8. Source & Assurance

The inventory below follows the video-derived application order before any redesign or rearrangement decision.

# 1. Portfolio Command Center — Charts

1 — PORTFOLIO COST POSITION

• Budget

• Earned Value

• Actual Cost

Compares Budget, Earned Value and Actual Cost on the selected common scope.

2 — MARGIN VS COST PERFORMANCE

• X = CPI

• Y = Revenue-based Gross Profit %

• Bubble Size = Contract Price

• Project

Shows cost efficiency and margin performance together, with contract size represented by bubble size.

3 — DIRECT VS INDIRECT ACTUAL COST

• Direct AC

• Indirect AC

• Project

Shows the reported direct-versus-indirect actual-cost mix for each selected project.

4 — REVENUE, ACTUAL COST & GROSS PROFIT

• Revenue

• Actual Cost

• Gross Profit

• Project

Places revenue-based profitability beside current actual cost for a fast executive margin comparison.

5 — PORTFOLIO CASHFLOW COMPARISON

• Gloria — Cash In

• Gloria — Cash Out

• THE BIG — Cash In

• THE BIG — Cash Out

• Source timeline / month

Compares cumulative cash-in and cash-out across the selected projects while retaining each project's source timeline.

# 2. CTO Analysis

6 — CTO TECHNICAL COST MATRIX — TABLE / MATRIX

• Project

• Contract Price

• Budget

• EV

• AC

• CV

• Selectable analysis metric

• Selected metric

• Highest reported value

• Peer difference

• High / low ratio

• In-table value bars

Executive peer-comparison matrix used to compare projects using a selected technical or cost metric.

7 — CTO MONTHLY COST COMPARISON

• Month

• Gloria

• THE BIG

• Selected monthly metric

• Cash In shown in the video

• Cumulative Cash Out shown in the video

• Common months only / All source months

• Latest comparable month

Compares SAP cost reports month by month, either on common comparable months or across the full available source history.

8 — CTO COST SCENARIO LAB

• Remaining Cost Stress

• Revenue Realization

• Indirect Cost Stress

• Current AC

• Scenario EAC

• Scenario Revenue

• Scenario Margin

Runs reversible what-if adjustments to show how cost, revenue and indirect-cost stress change the forecast position.

# 3. Projects

Selected project visible in the videos: GLORIA HOSPITAL — COST REPORT JUNE 2026

The project-level analysis then continues through Executive, Forecast Engineering, Cost Structure, Ledger & Controls, and Source & Assurance.

# 4. Executive

## Cost Position

9 — BUDGET VS EARNED VALUE VS ACTUAL COST — BY DIVISION

• Budget

• EV

• AC

• Division

Compares Budget, Earned Value and Actual Cost across project divisions.

10 — COST PERFORMANCE MAP

• X = % Completion

• Y = CPI to Date

• Bubble Size = Original Budget

• Work item / package

Maps completion against CPI while using original budget to represent the financial size of each item.

## Profit & Cashflow

11 — PROFITABILITY — THREE SOURCE METHODS KEPT SEPARATE

• Revenue-based Gross Profit

• GP Method / Net Profit

• Planned Gross Profit

Displays the three profitability methods separately rather than forcing them into one artificial profit number.

12 — MONTHLY CASHFLOW — CASH IN VS CASH OUT

• Cash In

• Cash Out

• Net

• Month

Shows monthly cash movement together with the resulting net cash position.

13 — CUMULATIVE CASHFLOW / S-CURVE

• Cumulative Cash In

• Cumulative Cash Out

• Month

Shows the cumulative development of project cash-in and cash-out through the reporting period.

## Resources & Efficiency

14 — DIRECT RESOURCE COST PARETO

• Resource / Source Category

• Actual Cost

• Material (Steel)

• Material (Concrete)

• Subcontractor

• Material

• Equipment

• Manpower

• Scaffolding

• Other resource classifications

Ranks actual resource costs so the largest resource-cost concentrations become immediately visible.

15 — WASTE EFFICIENCY

• Actual Waste %

• Budget Waste %

• Steel

• Concrete

Compares actual waste percentage against budget waste percentage for steel and concrete.

16 — ACCOUNTING — COST-CONTROL CLASSIFICATION BRIDGE

• Four EGP bridge components

• Accounting / ledger basis

• Cost-control classification

• Reconciliation gap

Bridges accounting-ledger cost classifications with the cost-control Direct Actual Cost view while retaining any remaining difference as a visible reconciliation gap.

The individual four x-axis labels were too small to read reliably in the mobile recording, so they are intentionally not invented here.

# 5. Forecast Engineering

## WBS Performance

17 — PROJECT SUMMARY / WBS — ALL 35 COST ITEMS — TABLE

• Item

• Division

• WBS Code

• Budget

• EV

• EAC

• ETC

• VAC

• Forecast Status

• Additional horizontally scrollable cost fields

Complete WBS performance register combining budget, earned value and forecast-status information at work-package level.

18 — PROJECT SUMMARY GROUP / TOTAL ROWS — TABLE

• WBS group

• Total Project

• Total Direct

• Total Indirect

• Total Fees & Sponsorship

• Aggregated financial values

• Budget / forecast status

Provides the WBS roll-up and total rows while keeping them inside the same performance family as the detailed WBS items.

## BOQ Actual Costs

19 — DETAILED BOQ RESOURCE EXPLORER — ACTUAL COST

• BOQ / Description

• Resource Category

• Actual Cost

• Search

• Detailed BOQ Sheet selector

Shows resource-level actual-cost evidence from the detailed BOQ sheets in both chart and detailed-table form.

## BOQ Forecast

20 — DETAILED BOQ FORECAST ANALYSIS — TABLE

• BOQ

• Budget Rate

• Forecast Rate

• Remaining Quantity

• BAC

• EV

• Remaining Budget

• ETC

Combines rate, remaining-quantity, earned-value and remaining-budget information to support the BOQ forecast.

# 6. Cost Structure

## Direct Costs

21 — DIRECT DETAILS — BOQ COMMERCIAL / EARNED-VALUE CONTRACT — TABLE

• BOQ

• WBS Code

• Description

• Unit

• Budget Rate

• Contract / commercial fields

• Quantities

• Invoice %

• Billing

• EV

• AC

• CV

• ETC

• EAC

• VAC

Detailed commercial and earned-value view of direct BOQ work.

## Indirect Costs

22 — INDIRECT COST DETAIL — ALL 59 CODED ROWS — TABLE

• Code

• Description

• Budget

• Actual Cost

• Variance

• Forecast fields

Maintains the official indirect-cost detail with budget, actual, variance and forecast information.

23 — INDIRECT COST POOLS — GRANULAR VS OFFICIAL — TABLE

• Source Classification

• Category

• Granular Pool

• Official classification

Keeps the granular and official indirect-cost classifications separate because they serve different workbook purposes.

## Allocations & Waste

24 — INDIRECT-DIRECT BREAKDOWN — DIRECT ALLOCATION DETAIL — TABLE

• Main Code

• Item

• Reallocated Equipment

• Other Cost allocations

• Resource / code detail

Shows the bridge of reallocated indirect items into direct-cost classifications while retaining code-level visibility.

25 — WASTE REPORT — COMPLETE SOURCE ROWS — TABLE

• % Actual Waste — average

• % Budget Waste — average

• Waste Cost — EGP

Retains the populated steel/concrete waste-source information rather than only showing an aggregated result.

26 — WASTE DETAIL — TABLE

• Type

• Item

• Actual Consumption

• Engineering Consumption

• Unit / supporting fields

Provides item-level consumption evidence behind the waste calculations.

# 7. Ledger & Controls

## Ledger Analytics

27 — ACTUAL EXPENSE TREND — SOURCE LEDGER

• Month

• Ledger Actual Cost

Shows the monthly actual-cost movement directly from the transaction ledger.

28 — EXPENSE SOURCE MIX

• Mat

• Subcontractor

• Petty Cash

• Wages

• Equ

• Transaction Total

Groups transaction-ledger cost by SAP source/type.

29 — TOP COST CODES BY ACTUAL LEDGER COST

• Main Code

• Actual Cost

Ranks the highest actual ledger-cost codes and allows a code to be used to drill into filtered transactions.

30 — LEDGER RECONCILIATION

• Four reconciliation scope totals

• EGP values

Keeps accounting and cost-control scopes separate and visibly comparable.

The four individual bar labels are not sufficiently legible in the video, so they are not assigned names here.

## Transactions

31 — EXPENSE TRANSACTIONS — TABLE

• S.N

• Main Code

• D / I

• Source

• Search

• Direct + Indirect / Direct / Indirect filter

• Source filter

• All sources

• Equ

• Mat

• Petty Cash

• Subcontractor

• Wages

Detailed ledger transaction register with classification, source filters and drill-down capability.

## Cost Code Register

32 — COST CODE LOOKUP — ALL 276 CODES — TABLE

• Code

• Description

• Search

Controlled searchable cost-code lookup kept separate from transaction analysis.

# 8. Source & Assurance

## Workbook Sources

33 — ADAPTIVE WORKBOOK SOURCE EXPLORER — TABLE / SOURCE EXPLORER

• Workbook Sheet

• Visible / Hidden status

• Cell count

• Detected tables

• Detected charts

• Populated cells

• Narrative / labels

• Source rows

Provides read-only evidence for every visible and hidden workbook sheet detected in the project source.

34 — SOURCE SHEET EXPLORER — RAW WORKBOOK CELLS — TABLE

• Row

• Workbook column

• Raw cell value

• Source sheet

• Source snapshot

Shows non-projected raw workbook cells so source evidence remains auditable rather than being replaced by the normalized application view.

## Source Visuals — Embedded Workbook Charts

The video explicitly indicates that six embedded chart objects were found.

35 — TOTAL ACTUAL COST

• Total Actual Cost

• Source/resource categories

• Subcontractor

• Living

• Equipment

• Invoices

• Petty Cash

• Wages

• Multiple material categories

Donut chart showing how total actual cost is distributed among the workbook's source/resource classifications.

36 — SOIL SETTLEMENT VS OTHER INDIRECT COST

• Soil Settlement

• Other Indirect Cost

Compares Soil Settlement cost with the remaining Other Indirect Cost.

37 — GENERAL COMPARISON

• Four workbook series

• Categories along the x-axis

• Series names displayed as Dashboard workbook cell-range references

Retained source-workbook comparison chart shown without rewriting the workbook-defined series.

38 — ACTUAL COST VS REVENUE

• Actual Cost

• Revenue

• Cum Actual Cost

• Cum Revenue

Compares period Actual Cost and Revenue together with their cumulative values.

39 — CASH FLOW

• No reporting-period chart data available

The embedded source chart is retained, but the screen explicitly states that source data is unavailable for the reporting period.

40 — CASH FLOW

• Cashin-Revenue

• Cashout-AC

• Cashin-Cum.

• Cashout-Cum.

Shows periodic and cumulative cash-in/revenue against cash-out/actual-cost values.

# Master Order Confirmed from the Videos

01. Portfolio Command Center

02. Charts

03. CTO Analysis

04. Projects

05. Executive

06. Cost Position

07. Profit & Cashflow

08. Resources & Efficiency

09. Forecast Engineering

10. WBS Performance

11. BOQ Actual Costs

12. BOQ Forecast

13. Cost Structure

14. Direct Costs

15. Indirect Costs

16. Allocations & Waste

17. Ledger & Controls

18. Ledger Analytics

19. Transactions

20. Cost Code Register

21. Source & Assurance

22. Data Quality

23. Workbook Sources

24. Source Visuals

This document is the video-derived inventory stage only. No redesign, priority change, or rearrangement recommendation has been applied.